Dr Qian Lu
Royal Society Short Industry Fellowship

---
Content
Content
- Progress update
- Plan for two weeks
- Other activities

---
A summary of the research
Project Plan
A summary of the research
Project Plan
Link to the project plan document

---
Progress Update
Progress Update
Simulation Preparation
  - Carmaker ROS bridge bug fix
    - Change datatype of intensity from 8 to 7
    - Modify the carmker_tf.launch
      - Baselink -> Fr1
      - Fr_lidarRSI->velodyne
    - Need to comment out ‘VehicleControl’ to follow defined trajectory
      - VehicleControl.Gas = gas:
      - VehicleControl.Brake = brake
      - VehicleControl.Steering.Ang = steer_ang

---
Progress Update
Hanging issues
Issue1: Need to launch baselink to localiser to set the localisation? Event the tf from baselink to velodyn can be established.
Issue2: Warnings, when launch ‘lane selection’

---
Progress Update
Hanging issues
Issue3: Vehicle speed is too slow, target speed set at 50, following is the speed profile
Need to look into sd_vehicle_interface package???
Speed Input: NDT_Localisation
Speed Input: Carmaker_Speed

---
Progress Update
Progress Update
Simulation Preparation
  - Use CM ground true of vehicle state/position as inputs
    - Use topic /current_velocity_cm as input to /pure_pursuit
    - Create new topic /current_pose_cm and use it as input to /pure_pursuit
      - New topic /current_pose_cm publish the following CM quantities
    - Need to modified the coordinate of /current_pose_cm to coordinate map
  - /pure_pursuit uses only two elements position.x and position.y in message geometry_msgs/PoseStamped

---
Progress Update
Progress Update
Test scenes and scenarios
  - Build MIRA AssuredHW track in Carmaker
    - Carmaker only support .Xodr, .KML and Heremap format
    - Use OpenStreetMap and convert it to opendrive (xodr)
    - Use google map
    - Use Carmaker model of the track developed by other project of CU (‘AssuredCAV’)
  - other scenarios
    - Single lane change
      - Velocity variation: 20-60km/h
      - Yaw rate variation:
    - Double lane change
      - Velocity variation: 20-60km/h
      - Yaw rate variation:
    - Simple turn
      - Velocity variation: 20-60km/h
      - Curvature variation: 0.6 – 4

---
Road curvature in England and Wales
Road curvature in England and Wales

---
Other activities
Add FS news to SD Social Media

---
Other activities
Other activities
Proposed three MSC projects to start from Jan
  - Articulated vehicle automated parking control
    - Efficient reverse manoeuvre control of tractor-trailer vehicle is very difficult because it is a complex mechatronic system with strong coupling and high nonlinearity. It is especially changelleging when manoeuvre through complex and narrow parking environment. The traditional control methods like PID control are difficult to achieved a satisfactory control performance when dealing with multiple constraints problem. However, model predictive control has been widely used in dealing with constraints issue on states and Input due to its many advantages, such as multi-constraint processing, rolling optimsation and good robustness. In this project, the student is expected to investigate into different control algorithm PID, MPC and explicit MPC and applied them into different challenging parking sceanrio of articulated vehicle, parallel, perpendicular parking, angle parking etc. The student need to analyse and make critical comparision on the performance of different of control mehtods on handling the parking scenario
  - CAV Autonomous Planning and Navigation using Lanelet2 & OpenStreetMap
    - Like human, autonomous vehicles need a map to plan and navigate the road network. OpenStreetMap is a map of the world, created by people like you and free to use under an open licence. Lanelet2 is a C++ library for handling map data for autonomous vehicle. This project aims to exploit the exisiting coversion tools to convert OpenStreetMap into Lanelet2 format, and integrate Lanelet 2 maps to an open-source software stack of autonomous vehicles (ASLAN) and design route planning algorithm on the Lanelet2 map. We will do this project on Simulation basis and however there is opportunity to deploy to the developed software to Coventry University's autonomous vehicle: StreetDrone.
  - CAV Object detection and fusion between Lidar and Video data
    - CAV use multiple sensors (camera, lidar, radars) to detect the environment. Similarly, the labotory autonomous vehicle 'Streetdrone' used by research centre CFTC has multiple sensors including Velodyne Lidar VLP32 and Stereo Camera ZED. In this project, we will exploiting the existing machine learning based object detection algorithm to detect road objects (e.g. vehicle, pedestrain, byciles) from video stream of ZED camera and fuse the result of detection from Velodyne Lidar.

---
Plan for the next
Plan for the next
- Simulation Preparation
  - Modified the simulation to use CM group true for control
  - Use CM generated trajectory instead of waypoint saver
- Create Test scene and scenarios in Carmaker
  - Build MIRA AssuredHW track in Carmaker
  - Other test scenarios
- Look into design and mathematical formulation of EMPC

---
Backups

---
Thank you